CHASING PAVEMENTS

Research Progress Tracker

____________________________________________________________

The Output Cost of Unpaved Roads in Sub-Saharan Africa

April 7, 2026

DRAFT — For Internal Use

# 1. Project Status Overview

| Phase | Description | Status | Notes |
| --- | --- | --- | --- |
| Phase 1 | Data Ingestion & Spatial Setup | COMPLETE (Tanzania) | OSM road network extracted, 677K km, surface classified. 2.2% paved, 66.5% unpaved, 31.3% unknown. |
| Phase 2 | Trade Cost Computation | COMPLETE (Tanzania) | Graph built (2M nodes, 95.8% connected). Baseline and counterfactual 186×186 trade cost matrices computed. Mean trade cost reduction: 31.2%. |
| Phase 3 | Model Calibration | NOT STARTED | Need WorldPop + VIIRS nightlights. Invert GE model for productivities and amenities. |
| Phase 4 | Counterfactual Analysis | NOT STARTED | Solve counterfactual equilibrium, compute welfare/GDP gains. |
| Phase 5 | Robustness & Extensions | NOT STARTED | Parameter sensitivity, cross-country scaling, optimal paving policy. |
| Paper | Writing & Figures | NOT STARTED | Target: working paper draft by week 24. |

# 2. Key Results (Preliminary — Tanzania)

677,579 km of roads across 1.1 million segments

Only 2.2% of road network is paved (14,994 km)

66.5% tagged as unpaved, 31.3% surface unknown

OSM surface tag coverage: 69% overall, ~100% for trunk/primary/secondary roads

70.4% of 186 admin-2 district pairs are connected through the road network

Average bilateral trade cost reduction from full paving: 31.2% (placeholder cost ratio c=3.0)

Range of reductions: 0% to 66.7%

Western and southern Tanzania gain the most; coastal/urban areas gain least

Ukerewe district (Lake Victoria) gains most (~60%); Zanzibar/Dar es Salaam gain least

# 3. Research Design Decisions

## Framing

Paper decomposes the "unobserved road quality" residual from Akbar, Couture, Duranton & Storeygard (2023), who show road quality explains a large share of speed differences across countries but treat it as a black box. We show that road surface type (paved vs. unpaved) is a first-order component of that residual.

## Cost Ratio Estimation

Will use the Google Maps Routes API (~$2K for 500K OD pairs across 8 countries) to estimate the unpaved speed penalty from simulated trips, following the Akbar et al. methodology validated in the AER. Currently using placeholder c_unpaved/c_paved = 3.0. The Essentials tier returns free-flow duration, which isolates road surface quality from congestion effects.

## Road Surface Data

Multiple ML-classified datasets are now available: Liu et al. (2026) in ESSD covering 50 African countries, Mapillary-based classifiers (Randhawa et al. 2025), and a Kenya-specific satellite study. OSM surface tags are surprisingly strong for Tanzania (69% coverage, ~100% on trunk/primary/secondary roads). Strategy: use best available source, validate against alternatives, defer final choice until all sources are compared.

## Reduced-Form Complement

Need empirical evidence beyond the structural model to anchor the GE estimates. Options include event studies around paving episodes (if temporal variation in surface classification can be obtained from satellite imagery), or correlations between paved road share and nightlights/economic outcomes at the district level, conditional on controls.

## Optimal Policy Extension

Beyond the "pave everything" benchmark, compute the marginal welfare contribution of each road segment if paved. This produces a priority ranking for a budget-constrained planner and a welfare frontier showing diminishing returns to paving investment. Comparison to actual paving patterns could reveal whether governments are paving the "right" roads.

# 4. Scaling Plan

| Country | OSM PBF Size | Status |
| --- | --- | --- |
| Tanzania | 703 MB | COMPLETE |
| Ethiopia | 105 MB | Pending |
| Kenya | 328 MB | Pending |
| Nigeria | 649 MB | Pending |
| Uganda | 346 MB | Pending |
| Ghana | 104 MB | Pending |
| Mozambique | 236 MB | Pending |
| Senegal | 99 MB | Pending |

# 5. Next Steps (Priority Order)

Download WorldPop population rasters and VIIRS nightlights for Tanzania; assign to admin-2 nodes

Calibrate GE model for Tanzania (invert for productivities and amenities)

Solve counterfactual equilibrium and compute headline welfare/GDP number

Scale Phases 1–2 pipeline to second country (Kenya or Ethiopia) to test generalizability

Set up Google Maps Routes API and run pilot queries for Tanzania OD pairs

Build reduced-form evidence (nightlights vs. paved share regressions)

Scale to all 8 countries

Robustness checks and optimal paving policy counterfactuals

Paper writing

# 6. Code Architecture

| File | Purpose |
| --- | --- |
| src/ingest.py | OSM PBF → road GeoDataFrame with surface classification |
| src/viz.py | Road network maps and surface coverage charts |
| src/network.py | Graph construction, shortest paths, bilateral trade cost matrices |
| src/viz_trade.py | Trade cost result visualizations (choropleths, scatter, rankings) |
| src/model.py | GE model calibration and counterfactual solver (TO BUILD) |
| src/analysis.py | Welfare computation, decomposition, cross-country regressions (TO BUILD) |